# ERPNext Deployment Implementation Plan for ULTRA MRF

# 1. Executive Summary & Deployment Mandate

This ERPNext Deployment Implementation Plan governs the end-to-end production deployment and enterprise rollout of ERPNext v16 and the Vehicle Management System (VMS) for ULTRA MRF.

The mandate covers the deployment of a centralized, real-time enterprise system across:

1 Corporate Headquarters: ULTRA MRF

8 Frontline Retail & Automotive Service Centers: Ultra MRF Dau Main, Ultra MRF Dau Annex, Ultra MRF San Fernando, Wheel Core, Automan Car Care Center, The Wheelhub, Ultra MRF Telebastagan, Ultra MRF Telebastagan 2.

3 Regional Distribution Hubs & Warehouses: Ultra MRF Warehouse Dau, San Fernando Warehouse, Ultra MRF Mexico Warehouse.

graph TD subgraph "Infrastructure & Hosting Tier" A1["Cloud Production VPS Host<br/>(38.247.138.224:10017)"] A2["Reverse Proxy & SSL<br/>(Caddy / Nginx)"] A3["PostgreSQL 15+ Enterprise DB<br/>(site1.local / 49MB Database)"] A4["Redis Cache & Celery/RQ Workers<br/>(Background task dispatch)"] end subgraph "Application Deployment Tier" B1["Frappe Framework v16 & ERPNext v16"] B2["Custom App: vehicle_management<br/>(Fleet, Job Orders, POS, Bins)"] B3["Touchscreen Web POS Terminal<br/>(/pos-terminal)"] B4["14 Executive & Branch Dashboards<br/>(/executive-dashboard)"] end subgraph "Branch Connectivity & Hardware Tier" C1["Dau Main & Annex Desks<br/>(Thermal printers, 2D guns, webcams)"] C2["San Fernando & Wheel Core<br/>(Bay tablets, diagnostic PCs)"] C3["Telebastagan & Automan Centers"] C4["Central Warehouses Dau / SF / Mexico<br/>(Inventory handhelds, 570 Bins)"] end A1 --> B1 A2 --> B1 A3 --> B1 A4 --> B1 B1 --> B2 B2 --> B3 B2 --> B4 B3 --> C1 B3 --> C2 B3 --> C3 B2 --> C4

# 2. Production Infrastructure & Deployment Topology

## A. Server Specifications & Production Stack

| Layer | Specification / Technology | Operational Role |
| --- | --- | --- |
| Host Environment | Linux VPS (Ubuntu 22.04 LTS / Debian 12) | Dedicated cloud server hosting all branch operations |
| Host IP / Port | 38.247.138.224:10017 | Public production endpoint |
| Web Server / Proxy | Caddy v2 / Nginx | SSL termination, reverse proxy, static asset caching |
| App Framework | Frappe Framework v16.x | Meta-data driven application server |
| ERP Application | ERPNext v16.x | Core Accounting, Stock, Buying, Selling, Fixed Assets |
| Automotive App | vehicle_management custom app | Fleet registry, Job Orders, POS, Bin locations |
| Database Engine | PostgreSQL 15+ (site1.local) | Relational database (full_restored.sql, 49MB schema) |
| In-Memory Cache | Redis Cache & Redis Queue | Session caching, background worker queue management |
| Process Supervisor | Supervisor / Podman Systemd | Process auto-restart and zero-downtime worker orchestration |
| File Storage | Local NVMe + Offsite Backup Sync | Stores vehicle inspection photos, QR badges, and documents |

## B. Network & Firewall Configuration

Port 80 / 443: Inbound HTTPS traffic from branch cash registers and executive laptops.

Port 10017: Direct application port reverse-proxied via Caddy.

Port 22: SSH restricted to authorized DevOps IP keys.

Port 5432 (PostgreSQL): Bound strictly to localhost (127.0.0.1) and internal container network. External database access is disabled.

# 3. Multi-Company Enterprise Configuration

The deployment configures 12 corporate company records in ERPNext, enforcing multi-company financial isolation while allowing corporate consolidation:

graph TD HQ["ULTRA MRF (Corporate Parent Company)"] subgraph "Retail & Automotive Service Centers" C1["Ultra MRF Dau Main (Flagship)"] C2["Ultra MRF Dau Annex"] C3["Ultra MRF San Fernando"] C4["Wheel Core"] C5["Automan Car Care Center"] C6["The Wheelhub"] C7["Ultra MRF Telebastagan"] C8["Ultra MRF Telebastagan 2"] end subgraph "Regional Logistics & Warehouses" W1["Ultra MRF Warehouse Dau"] W2["San Fernando Warehouse"] W3["Ultra MRF Mexico Warehouse"] end HQ --> C1 HQ --> C2 HQ --> C3 HQ --> C4 HQ --> C5 HQ --> C6 HQ --> C7 HQ --> C8 HQ --> W1 HQ --> W2 HQ --> W3

## Configuration Matrix per Company:

Chart of Accounts (COA): Standardized Philippine Chart of Accounts template customized with automotive cost centers.

Cost Center Tagging: Unique cost center assigned per branch (e.g. UMDM, UMDA, UMSF, WC, ACCC, TWH, UMT).

Warehouses: Default warehouse mapped per location (e.g. Stores - UMDM, Stores - UMDA, Stores - UMSF).

POS Profiles: Dedicated profile per physical cash register specifying company warehouse, payment modes, and price list.

Tax Category: 12% Philippine Value Added Tax (VAT) configured on sales invoices, POS invoices, and purchase orders.

# 4. Master Data Migration & Cutover Deployment

The cutover deployment migrates all verified legacy data into ERPNext with automated data normalization:

graph LR D1["1. Legacy Extraction<br/>(SQL Dump / 49MB)"] --> D2["2. Data Normalization<br/>(Clean spaces, Validate plates)"] D2 --> D3["3. Master Import<br/>(38,654 Vehicles, 570 Bins)"] D3 --> D4["4. Asset Capitalization<br/>(10 Workshop Machines)"] D4 --> D5["5. Opening Balances<br/>(Stock, AR, AP, GL)"]

## A. Data Ingestion Volumes & Validation Rules:

Customer Vehicle Registry (38,654 Records):

Normalized via batch_clean_vehicles.py to eradicate multi-space corruptions (e.g. "JOAN  CHIIETE" $\rightarrow$ "JOAN CHIIETE").

Validated plate numbers, engine numbers, and chassis/VIN numbers.

Relational links confirmed to 38,000+ customer records.

Warehouse Bin Locations (570 Records):

Complete hierarchy: Aisle $\rightarrow$ Rack $\rightarrow$ Shelf $\rightarrow$ Bin slotting.

Item Master Catalog:

Tires (TBR, PCR, SUV), alloy wheels, lubricants (motor oil, gear oil, coolant), replacement parts, and labor services.

Standard units of measure (PC, SET, LITER, DRUM) and barcodes indexed.

Fixed Assets (10 Capitalized Machines):

Capitalized workshop machinery (3D Wheel Aligners, Tire Changers, Balancers, 2-Post Lifts, AC Stations) with monthly straight-line depreciation schedules.

Opening Financial & Stock Balances:

Opening inventory imported via Stock Reconciliation per branch warehouse.

Opening trade receivables and payables imported via Opening Journal Entry.

# 5. Branch Hardware & Peripherals Deployment

Each physical branch location is equipped with standardized hardware profiles:

graph TD subgraph "Branch Hardware Architecture" K1["Cashier Counter PC / All-in-One Touchscreen"] K2["2D USB/Bluetooth Barcode Scanner Gun<br/>(Tire labels & Part barcodes)"] K3["Webcam / Integrated Camera<br/>(Cashier badge & Receiver QR scanner)"] K4["80mm Thermal Receipt Printer<br/>(ESC/POS instant receipt generation)"] K5["Electronic Cash Drawer (RJ11 trigger)"] K6["Mobile Tablet / Bay Laptop<br/>(Technician Job Orders & Digital Inspection)"] end K1 --- K2 K1 --- K3 K1 --- K4 K4 --- K5 K1 -.-> K6

## Hardware Deployment Checklist per Branch:

Network: Dual ISP broadband connection (Primary Fiber + 4G/LTE Backup Failover).

Cashier Station:

Minimum PC specs: Intel Core i3 / 8GB RAM / 128GB SSD / Windows 10/11 or Ubuntu.

Chrome/Edge browser pinned to http://38.247.138.224:10017/pos-terminal.

Cashier camera tested with 📷 Scan QR Code modal.

Thermal printer configured with custom 80mm ESC/POS print format.

Service Bay Stations:

Android/iOS tablet or rugged laptop accessing /desk/vehicle-job-order.

Digital camera permissions active for multi-point vehicle intake photos.

# 6. Phased Rollout Schedule (14-Week Plan)

The deployment follows a phased rollout to mitigate operational risks across branches:

gantt title ULTRA MRF ERPNext Deployment Schedule dateFormat YYYY-MM-DD section Wave 1: Pilot & Hub Server Setup & PostgreSQL Migration :done, w1_1, 2026-09-01, 2026-09-10 Pilot Cutover: Dau Main & Warehouse Dau :active, w1_2, 2026-09-11, 2026-09-25 section Wave 2: Core Branches Dau Annex & San Fernando Cutover :w2_1, 2026-09-26, 2026-10-10 Wheel Core & San Fernando Warehouse :w2_2, 2026-10-05, 2026-10-20 section Wave 3: Expansion Centers Telebastagan 1 & 2 Cutover :w3_1, 2026-10-21, 2026-11-05 Automan & The Wheelhub Cutover :w3_2, 2026-11-01, 2026-11-15 Mexico Warehouse Integration :w3_3, 2026-11-10, 2026-11-20 section Wave 4: Full Enterprise Enterprise Review & Hypercare Sign-off :w4_1, 2026-11-20, 2026-12-05

## Deployment Waves:

Wave 1 (Pilot — Weeks 1 to 4):

Host infrastructure validation (38.247.138.224:10017).

Live pilot rollout at Ultra MRF Dau Main and central distribution hub Ultra MRF Warehouse Dau.

Validate high-speed counter POS, warehouse material transfers, and GL posting.

Wave 2 (Core Branches — Weeks 5 to 8):

Rollout to Ultra MRF Dau Annex, Ultra MRF San Fernando, Wheel Core, and San Fernando Warehouse.

Inter-branch replenishment and stock movement testing.

Wave 3 (Expansion Centers — Weeks 9 to 12):

Rollout to Automan Car Care Center, The Wheelhub, Ultra MRF Telebastagan, Ultra MRF Telebastagan 2, and Ultra MRF Mexico Warehouse.

Enable complete multi-branch executive dashboard consolidation.

Wave 4 (Stabilization & Hypercare — Weeks 13 to 14):

Full production sign-off, SLA governance, and operational handover.

# 7. Cutover Weekend Runbook (Minute-by-Minute Protocol)

The final cutover for each branch is executed over a weekend using this exact runbook:

graph TD T1["Friday 18:00 - Cutover Freeze<br/>Halt all legacy sales and stock writes"] --> T2["Friday 19:00 - Final Data Extraction<br/>Extract closing balances and customer receivables"] T2 --> T3["Saturday 08:00 - Physical Stock Audit<br/>Wall-to-wall physical inventory count at branch"] T3 --> T4["Saturday 14:00 - Master Ingestion<br/>Import Opening Stock & Balances into ERPNext"] T4 --> T5["Saturday 18:00 - Financial Reconciliation<br/>Trial Balance & Stock Value verified by Finance"] T5 --> T6["Sunday 09:00 - Dry Run & Hardware Check<br/>Simulate 5 counter sales, test printers and scanners"] T6 --> T7["Sunday 16:00 - Go/No-Go Decision<br/>Executive Sponsor & Steering Committee sign-off"] T7 --> T8["Monday 07:30 - Live Production Go-Live<br/>Cashiers log in, shift opens, live customers served"]

| Timeline | Milestone / Action | Responsible Party | Success Criteria |
| --- | --- | --- | --- |
| T-48h (Fri 18:00) | Freeze legacy billing systems; announce cutover | Project Manager | Legacy systems set to read-only |
| T-36h (Sat 08:00) | Physical inventory cycle count across branch bays | Storekeeper / Audit | Signed count variance sheets |
| T-24h (Sat 14:00) | Ingest opening stock into Stores - [BRANCH] | Technical Architect | tabBin actual qty matches audit count |
| T-16h (Sat 18:00) | Post opening AR/AP and trial balance journals | Functional Consultant | Balance Sheet debits equal credits |
| T-12h (Sun 09:00) | Hardware sanity test: 2D guns, receipt printers | Branch Super User | Test receipt prints without errors |
| T-4h (Sun 16:00) | Executive Go/No-Go evaluation meeting | Steering Committee | Formal GO decision approved |
| T-0 (Mon 07:30) | Open live cash registers via POS Opening Entry | Cashiers / Branch Mgr | First live vehicle serviced & billed |

# 8. User Acceptance Testing (UAT) Scripts

Before any branch cutover, staff must pass the following standardized UAT scenarios:

## UAT-01: Front Desk Express POS Counter Sale

Tester: Cashier

Steps:

Open /pos-terminal.

Scan Cashier QR ID Badge or type credentials. Verify active shift loads.

Enter customer plate number (e.g. CAZ4232). Verify make and model auto-populate.

Toggle In Stock: ON. Verify only on-hand branch warehouse items appear.

Add 2 tires and 1 oil filter. Choose payment method: Cash. Enter ₱5,000 tender.

Click Complete Sale.

Expected Result: System creates Vehicle POS Invoice, auto-submits ERPNext POS Invoice, decrements tabBin.actual_qty, writes General Ledger entries, and prints 80mm receipt with change calculation.

## UAT-02: Workshop Vehicle Job Order Lifecycle

Tester: Service Advisor / Technician

Steps:

Create Vehicle Inspection from template. Check tires, brakes, battery. Attach photo.

Create Vehicle Job Order in status Draft. Add labor (PMS) and parts.

Change status to In Progress. Technician executes mechanical work.

Change status to Completed and release vehicle.

Expected Result: Job order logs technician labor hours, calculates total parts and labor, and routes to cashier for settlement.

## UAT-03: Material Issue QR Safety Handover

Tester: Warehouse Custodian

Steps:

Create Stock Entry (Material Issue) to release 4 tires to Bay 2.

Click Submit. Receiver QC modal intercepts.

Technician presents employee QR badge to camera and snaps photo evidence.

Click Verify & Submit.

Expected Result: Transaction blocked if badge is invalid; submits cleanly with attached photo proof when badge is verified.

# 9. Backup, Disaster Recovery & High Availability

To ensure continuous operation without data loss:

graph TD Prod["Production PostgreSQL Database<br/>(Live writes at 38.247.138.224)"] subgraph "Backup & Redundancy Architecture" B1["Local Automated Snapshots<br/>(Every 6 Hours via pg_dump)"] B2["Offsite Daily Backup Mirror<br/>(Encrypted sync to secondary cloud storage)"] B3["Google Drive Master Backup<br/>(Automated daily export via notebook/API)"] end Prod --> B1 Prod --> B2 Prod --> B3

## Backup & Recovery Metrics:

Recovery Point Objective (RPO): < 6 Hours (maximum potential data exposure in catastrophic hardware failure).

Recovery Time Objective (RTO): < 1 Hour (server restoration from complete snapshot).

Automated Backup Schedule:

Hot Database Dumps: Executed every 6 hours (00:00, 06:00, 12:00, 18:00).

Nightly Offsite Archive: Compressed .dump files uploaded to offsite storage and Google Drive.

Retention Policy: Retain 7 daily snapshots, 4 weekly snapshots, and 12 monthly archives.

# 10. Post-Deployment Hypercare & Operations Governance

Following production go-live, the system enters a 30-day Hypercare Period:

## Support Escalation Hierarchy:

Level 1 (Immediate On-Site Support): Branch Super User / Lead Cashier resolves minor printer jams, badge scans, or user password resets. Response time: < 15 minutes.

Level 2 (ERP Functional Support): Functional Consultant resolves invoice cancellations, pricing rule adjustments, or customer credit limit overrides. Response time: < 30 minutes.

Level 3 (DevOps & Core Architecture): Antigravity Technical Architect handles database lockups, Caddy proxy routing, or code exceptions. Response time: < 1 hour.

## Operational Auditing & SLA Reviews:

Daily: End-of-day POS drawer cash balancing and unsubmitted draft reconciliation.

Weekly: Warehouse cycle count variance audit and stock ledger balance check.

Monthly: Fixed asset depreciation verification, BIR VAT tax summary audit, and executive dashboard financial review.